Basic Skills Projects: 2012-2013 Timeline & Responsibilities

The following are the establish guidelines for Basic Skills Initiative funded projects as per the Basic Skills Coordinating Committee, and defines who gets what done by when. Earlier timelines are possible given the nature of your work. The goal is to complete one assessment cycle during each fiscal year of funding.

Color Key:

Project Managers (PM)	Fall Assessment Schedule

Research (RIE)	Spring Assessment Schedule

| Responsibility | Completion Date |
| --- | --- |
| Notification of funding approval for projects | 4th Friday, June |
| Consultation: If needed, submit Research Request Form to RIE regarding Columns 1, 2, and 3 Meet with PM to construct Columns 1, 2, and 3. | 4th Friday, September OR 4th Friday, October |
| Completion of Columns 1 (Goals), 2 (Outcomes), and 3 (Assessment Methodology): Column 1, 2, and 3 entered into TracDat | 1st Friday, October OR 1st Friday, November |
| Mid-Year Reports for All projects: Complete mid-year report Request additional funds if needed Submit report to Instruction Office, Basic Skills | 1st Friday, March |
| Assessment: Implementation of Assessment Method | 1st Friday, December OR 2nd Friday, June |
| Data Collection and Submission: Collect data Transcribe qualitative data for data sets containing 50+ total data points Request RIE involvement in Data Collection (e.g., Scanning, Banner) | 3rd Friday, December OR 3rd Friday, June |
| Data Compilation, Analysis, and Review: If requested, scan or compile data If appropriate, perform statistical measures Submit data to PM for review If needed, engage RIE in dialogue about questions and concerns | 4th Friday, January OR 2nd Friday, August |
| Completion of Column 4 (Summary of Data): Enter Column 4 into TracDat | 1st Friday, February OR 4th Friday, August |
| Completion of 5 (Use of Results): Enter Column 5 into TracDat | 3nd Friday, February OR 2nd Friday, September |
| Basic Skills Report: RIE compiles all Basic Skills Initiative assessment entered into TracDat | 4th Friday, September |