Committee Goal and Progress Report

2008-2009

Committee name:	Budget Committee

Name of person completing the report:    	Kerry Martinez

Instructions:    By November 15, 2008:   Complete Columns 1 and 2; submit electronically to dcasteel@mtsac.edu (on behalf of the President’s Advisory Council.)    By May 1, 2009:  Complete Column 3 and submit electronically to dcasteel@mtsac.edu (on behalf of the President’s Advisory Council.)

# (EXPAND AS NECESSARY)

| Committee Goal | Link to College Goal # | Completed Outcomes/Accomplishments (descriptive bullet list) |
| --- | --- | --- |
| GOAL # 1: Develop guidelines for budget reduction. | 1,2,10 | Completed and sent to the campus community on December 8, 2008. |
| GOAL # 2: Assess and update the Budget Allocation Process. Include PIE process to integrate campus-wide planning processes. | 1,2,10 | Will be completed in June and sent to the President’s Advisory Council for review on August 5, 2009. |
| GOAL # 3: Evaluate and revise the Purpose and Function of the Budget Committee. | 1,2,10 | Completed and sent to the President’s Advisory Council for review on March 4, 2009. |
| GOAL # 4: Strengthen communication with the Campus Community regarding budget issues. Monthly communication to the Campus from the Budget Committee. | 6,7 | Has not been completed as of June 2009. This item is ongoing in Budget Committee. |