| **2020-21** |
| --- |
| **Winter 2021** | * ISER timeline drafted
 |
| **Spring 2021** | * Accreditation Steering Committee (ASC) reviews Lessons Learned
* Faculty Accreditation Coordinator appointed
* ISER timeline reviewed and approved by ASC
* ASC Leadership Workgroup formed (Accreditation Core Team - ACT)
 |
| **2021-22** |
| **Fall 2021** | * Self-Evaluation launch & training – October 22, 2021 (Members of Accreditation Steering Committee and campus leaders participated in a training workshop led by Gohar Momjian.) Link Presentation
* Accreditation theme contest launched
* ASC chooses accreditation theme Link Video and writing structure
* Re-alignment of ISER Standards to governance groups and experts
* Weaving Team members identified and invited to participate
 |
| **Winter 2022** | * ISER timeline revised ISER Timeline
 |
| **Spring 2022** | * Update to campus community at FLEX Day Link Presentation
* ISER Training for Weaving (Writing) Team members Link Presentation
* ACT participates in ACCJC Annual Conference and Webinar Series
* Board of Trustees accreditation training Link Presentation
* Student Weaving Team member training Link Presentation
* Weaving Team communication and evidence collection process is established in collaboration with IT experts Link Evidence Guide
* Monthly Accreditation Forums engage campus community in the accreditation process, (Accreditation with Class!, DE/DL in Accreditation)
* ACT liaisons support Weaving Team activities
* Weaving Teams collect evidence and submit initial drafts
* Finishing Team member recruitment
 |
| **2022-23** |
| **Summer 2022** |  |
| **Fall 2022** |  |
| **Winter 2023** |  |
| **Spring 2023** |  |
| **2023-24** |
| **Summer 2023** |  |
| **Fall 2023** |  |
| **Winter 2024** |  |
| **Spring 2024** |  |
| **2023-24** |
| **Summer 2024** |  |